## Slide 1: Implementation Plan for Food Security Forecasting Model (F Model) Information in AFSIS
Shoji KIMURA
Expert of ASEAN Food Security Information System (AFSIS) Project

## Slide 2
  Purpose
  Desires to promote the Food Security Forecasting Model, in the field of standardization and conformity assessment on the basis of equality and mutual benefits.
  Recognizing that such cooperation shall promote economic partnership and support friendly relationships between member countries.

## Slide 3: 2. Period
2013 - 2015

## Slide 4: 3. Activity
3-1. To create the mid-long term supply and demand forecasting information.
3-2. To broaden the necessary data for creating mid-long term supply and demand forecasting information.

## Slide 5: 3. Activity (2)
3.1 Creating supply and demand forecasting information
3.1.1 Learning and creating
[first year] Understanding and learning forecasting method
Training Homework Workshop (presentation)
[Second year] Learning the forecasting model and creating supply and demand forecasting information using F Model
Training Homework Workshop (presentation)
[Third year] Creating and Analyzing supply and demand forecasting information
Training Homework Workshop (presentation)

## Slide 6: 3. Activity (3)
3-1 Creating supply and demand forecasting information
3-1-2 Developing F Model
[First year]
Developing F Model
Developing by Japan International Research Center for Agricultural Sciences (JIRCAS)

## Slide 7: 3. Activity (4)
3-2 Broadening necessary data
3-2-1 “Guideline for collecting data” for F Model
[First year – Second year]
3-2-2 Collecting the data based on guideline
[First year – Third year]
3-2-3 Improving AFSIS Database
[Third year]

## Slide 8: 4. Activity Schedule
[First year]
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
 | Investigating meeting Workshop Training Workshop |  |  |  |  |  |  |  |  |  |  | 
A F S I S | Developing F Model (JIRCAS) Guideline for data (draft) Guideline for rice Guideline for other crops |  |  |  |  |  |  |  |  |  |  | 
M E M B E R C O U N T R I E S | Homework Creating forecasting information using regression formula Forecasting report Examine guideline Data Collecting |  |  |  |  |  |  |  |  |  |  | 

## Slide 9: 4.Activity Schedule (2)
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
 | Training Workshop |  |  |  |  |  |  |  |  |  |  | 
A F S I S | F Model review (JIRCAS) F Model parameter (JIRCAS) Guideline for meats Improving statistical method (Supporting for target countries) |  |  |  |  |  |  |  |  |  |  | 
M E M B E R C O U N T R I E S | Homework Creating forecasting information using F Model Extending target commodities Forecasting report Data collecting |  |  |  |  |  |  |  |  |  |  | 
[Second year]

## Slide 10: 4. Activity Schedule (3)
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
 | Training Workshop |  |  |  |  |  |  |  |  |  |  | 
A F S I S | F Model parameter review (JIRCAS) Improving Database Announcement of Forecasting Information in ASEAN Improving statistical method (Supporting for Target countries) |  |  |  |  |  |  |  |  |  |  | 
M E M B E R C O U N T R I E S | Providing new data to AFSIS Creating forecasting information using model (reflecting agricultural policy) Forecasting report Date collecting |  |  |  |  |  |  |  |  |  |  | 
[Third year]
Homework

## Slide 11
Comparison of Present database and New database |  |  |  |  |  |  |  |  |  |  | 
No. | Item | No. | Item | No. | Item | No. | Item | No. | Item | No. | Item
1 | Paddy harvested area | 44 | Cassava exports quantity | 5 | Soybean seed | 128 | Soybean processing use | 170 | Beef meat domestic supply | 212 | Chicken meat import value total
2 | Maize harvested area | 45 | Sugarcane exports quantity | 87 | Paddy waste | 129 | Rice other use | 171 | Buffalo meat domestic supply | 213 | Population
3 | Cassava harvested area | 46 | Soybean exports quantity | 88 | Maize waste | 130 | Maize other use | 172 | Pork meat domestic supply | 214 | GDP, real
4 | Sugarcane harvested area | 47 | Paddy imports value | 89 | Cassava waste | 131 | Cassava other use | 173 | Chicken meat domestic supply | 215 | GDP, nominal
5 | Soybean harvested area | 48 | Maize imports value | 90 | Sugarcane waste | 132 | Sugarcane other use | 174 | Beef meat food use | 216 | GDP, nominal (USD)
6 | Paddy planted area | 49 | Cassava imports value | 91 | Soybean waste | 133 | Soybean other use | 175 | Buffalo meat food use | 217 | GDP deflator
7 | Maize planted area | 50 | Sugarcane imports value | 92 | Population domain | 134 | Rice beginning stocks | 176 | Pork meat food use | 218 | CPI
8 | Cassava planted area | 51 | Soybean imports value | 93 | Domestic Consumption | 135 | Maize beginning stocks | 177 | Chicken meat food use | 219 | 
9 | Sugarcane planted area | 52 | Paddy exports value | 94 | Number and area of agricultural holdings | 136 | Cassava beginning stocks | 178 | Beef meat food use per capita | 220 | 
11 | Soybean planted area | 53 | Maize exports value | 95 | Labor Force of persons | 137 | Sugarcane beginning stocks | 179 | Buffalo meat food use per capita | 221 | 
12 | Paddy production | 54 | Cassava exports value | 96 | Gross Domestic Product (GDP) | 138 | Soybean beginning stocks | 180 | Pork fmeat ood use per capita | 222 | 
13 | Maize production | 55 | Sugarcane exports value | 97 | Per capita Gross Value Added (GVA) | 139 | Rice ending stocks | 181 | Chicken meat fooduse per capita | 223 | 
14 | Cassava production | 56 | Soybean exports value | 98 | Rice producer price | 140 | Maize ending stocks | 182 | Beef meat other use | 224 | 
15 | Sugarcane production | 57 | Paddy imports | 99 | Maize producer price | 141 | Cassava ending stocks | 183 | Buffalo meat other use | 225 | 
16 | Soybean production | 58 | Maize imports | 100 | Cassava producer price | 142 | Sugarcane ending stocks | 184 | Pork meat other use | 226 | 
17 | Paddy yield | 59 | Cassava imports | 101 | Sugarcane producer price | 143 | Soybean ending stocks | 185 | Chicken meat other use | 227 | 
18 | Maize yield | 60 | Sugarcane imports | 102 | Soybean producer price | 144 | Pig producer price | 186 | Beef stock change | 228 | 
19 | Cassava yield | 61 | Soybean imports | 103 | Rice retail price | 145 | Cattle producer price | 187 | Buffalo meat stock change | 229 | 
20 | Sugarcane yield | 62 | Paddy exports | 104 | Maize retail price | 146 | Buffalo producer price | 188 | Pork stock change | 230 | 
21 | Soybean yield | 63 | Maize exports | 105 | Cassava retail price | 147 | Chicken producer price | 189 | Chicken meat stock change | 231 | 
22 | Paddy farmgate price | 64 | Cassava exports | 106 | Sugarcane retail price | 148 | Beef producer price | 190 | Beef meat beginning stocks | 232 | 
23 | Maize farmgate price | 65 | Sugarcane exports | 107 | Soybean retail price | 149 | Buffalo meat production price | 191 | Buffalo meat beginning stocks | 233 | 
24 | Cassava farmgate price | 66 | Soybean exports | 108 | Rice, wet season harvested area | 150 | Beef retail price | 192 | Chicken meat beginning stocks | 234 | 
25 | Sugarcane farmgate price | 67 | Paddy stock changes | 109 | Rice, dry season harvested area | 151 | Buffalo meat retail price | 193 | Beef meat ending stocks | 235 | 
26 | Soybean farmgate price | 68 | Maize stock changes | 110 | Rice, upland harvested area | 152 | Pork retail price | 194 | Buffalo meat ending stocks | 236 | 
27 | Paddy crop calendar | 69 | Cassava stock changes | 111 | Rice, wet season yield | 153 | Chicken retail price | 195 | Pork meat ending stocks | 237 | 
28 | Maize crop calendar | 70 | Sugarcane stock changes | 112 | Rice, dry season yield | 154 | Cattle inventory number | 196 | Chicken meat ending stocks | 238 | 
28 | Cassava crop calendar | 71 | Soybean stock changes | 113 | Rice, upland yield | 155 | Buffalo total inventoy number | 197 | Beef meat export quantity | 239 | 
30 | Sugarcane crop calendar | 72 | Paddy domestic supply | 114 | Rice, wet season production | 156 | Pig total inventory number | 198 | Buffalo meat export quantity | 240 | 
31 | Soybean crop calendar | 73 | Maize domestic supply | 115 | Rice, dry season production | 157 | Chicken total inventory number | 199 | Pork meat export quantity | 241 | 
32 | Paddy cost of production | 74 | Cassava domestic supply | 116 | Rice, milled production | 158 | Cattle slaughtered number | 200 | Chicken meat export quantity | 242 | 
33 | Maize cost of production | 75 | Sugarcane domestic supply | 117 | Rice food use | 159 | Buffalo slaughtered number | 201 | Beef meat export value total | 243 | 
34 | Cassava cost of production | 76 | Soybean domestic supply | 118 | Maize food use | 160 | Pig slaughtered number | 202 | Buffalo meat export value total | 244 | 
35 | Sugarcane cost of production | 77 | Paddy feed use | 119 | Cassava food use | 161 | Chicken slaughtered number | 203 | Pork meat export value total | 245 | 
36 | Soybean cost of production | 78 | Maize feed use | 120 | Sugarcane food use | 162 | Beef meat per slautered animal | 204 | Chicken meat export value total | 246 | 
37 | Paddy imports quantity | 79 | Cassava feed use | 121 | Soybean food use | 163 | Buffalo meat per slaughtered animal | 205 | Beef meat import quantity | 247 | 
38 | Maize imports quantity | 80 | Sugarcane feed use | 122 | Rice food use per capita | 164 | Pork meat per slaughtered animall | 206 | Buffalo meat import quantity | 248 | 
39 | Cassava imports quantity | 81 | Soybean feed use | 123 | Maize food use per capita | 165 | Chicken meat per slaughtered animal | 207 | Pork meat import quantity | 249 | 
40 | Sugarcane imports quantity | 82 | Paddy seed | 124 | Cassava food use per capita | 166 | Beef meat production | 208 | Chicken meat import quantity | 250 | 
41 | Soybean imports quantity | 83 | Maize seed | 125 | Sugarcane food use per capita | 167 | Buffalo meat production | 209 | Beef meat import value total | 251 | 
42 | Paddy exports quantity | 84 | Cassava seed | 126 | Soybean food use per capita | 168 | Pork meat production | 210 | Buffalo meat import value total | 252 | 
43 | Maize exports quantity | 85 | Sugarcane seed | 127 | Sugarcane processing use | 169 | Chicken meat production | 211 | Pork meat import value total | 253 | 

## Slide 12: 5.Implementation Structure
Project Manager
Consultant FAO Other Institution
Training Workshop
Developing F Model Broadening necessary data Improving Database
JIRCAS AFSIS Expert AFSIS Secretariat
FP Member FP Member
Training
Workshop
Trainees

## Slide 13
6. Responsibilities of Member countries (1)
6-1 Member countries collaborate in the implementation and development of forecasting information conducted in ASEAN Member States.
6-2 Member countries must prepare the working group for F Model activity. This working group consists of a chief (FP member) and two trainee staffs.

## Slide 14
  6. Responsibilities of Member countries (2)
6-3 Trainees are requested as follows:
Bachelor level of statistics, economics, agriculture or any related field.
Have a basic knowledge of Regression technique
Responsible for agriculture statistics
Fluent in English, written and spoken is a must
It must be less than 50 years
6-4 Trainee staffs have to work to the exercises that indicated by training after the training.
6-5 Member countries are requested to prepare the data according to the “guideline for collecting data” for F Model activity.

## Slide 15
7. Continuity to obtain and tackle
To guarantee a prompt response and dissemination of acquired knowledge and information with the members of working group, pioneering participant of this training would be responsible to obtain and tackle the succeeding trainings to be conducted.
Training certificate would be given to a trainee who complete the presentation in workshop by each year.

## Slide 16
FAO TCPFP Workshop and the First AFSIS F Model Training Program
Time | July 9 Tue | July 10 Wed | July 11 Thu | July 12 Fri | July 13 Sat
9:00 – 10:30 | (AFSIS F Model Training) Orienteering Opening session Presentation -Keynote lecture (Dr. Aprichart Pongsrihadulchai) Implementation plan for F Model activity (Mr. Kimura) | Lecture and practice -Single equation model Testing Function type (Dr. Kusano, JIRCAS) | Lecture -Agricultural Economic Situation- (Dr. Aree Wiboonpongse) Chiang mai university | Lecture and practice -Single equation model- Elasticity Projection (Dr. Kusano, JIRCAS) | Presentation and discussion -Data definition for F Model (rice) (Mr. Kimura)
11:00 – 12:30 |  |  |  |  | 
13:30 – 15:00 | Lecture and practice -Single equation model- Basic statistics Regression (Dr. Kusano, JIRCAS) | Lecture -Fundamental regression- (Dr. Aree Wiboonpongse) Chiang mai university | Lecture -Econometric Apply- (Dr. Aree Wiboonpongse) Chiang mai university | Lecture and practice -Single equation model- Dummy and policy Further development (Dr. Kusano, JIRCAS) | Homework for Trainee (Dr. Kusano, JIRCAS, Mr. Kimura) Closing session
15:30 – 17:00 |  |  |  |  | 

## Slide 17
Dr. Eiichi Kusano
Researcher with fixed term
Japan International Research Center for Agricultural Sciences, Tsukuba, Japan
Educational background:
Name and place | Years attended |  | Degrees | Main subjects
 | From | To |  | 
Tokyo University of Agriculture and Technology, Tokyo, Japan | 2005 | 2008 | Ph.D. (Doctor of Agriculture) | Comprehensive development study on semi-arid area in China
Ibaraki University, Ibaraki, Japan | 2003 | 2005 | Master of Agriculture | Study on surplus labor in China
Ibaraki University, Ibaraki, Japan | 1999 | 2003 | Bachelor of Agriculture | Rural development model study in Japan
Instructor (permanent)

## Slide 18
Dr. Aree Wiboonpongse
Professor
Agricultural Economics and Extension,
Faculty of Agriculture,
Chiangmai University
Educational background:
Name and place | Years attended | Degrees
University of Illinois , United States Of America | 1981 | Ph.D. (Agricultural Economics)
The Australia National University, Australia | 1977 | M.S. (Agricultural Development Economics)
Kasetsart University , Thailand | 1969 | B.A. (Cooperative Economics)
Instructor (non- permanent)